## Slide 1
Saint Camillus Church
Bell Tower
Masonry Assessment
CPARL Review
12 September, 2025

## Slide 2: Saint Camillus Church Bell Tower Masonry Assessment
Emergency masonry repairs Fall 2023
Engineering review Spring 2024
Carillon shut down for safety Summer 2024
Scope of work developed and bid to contractors Summer 2024
Fundraising Fall 2024 - Present
CPARL Facilities Committee oversight Fall 2024 – Present
Overview
East facade

## Slide 3: Saint Camillus Church Bell Tower Masonry Assessment
Emergency masonry repairs
Masonry repointing and anchoring, portions of south and east sides
Replace portions of damaged sealant, south and east sides

## Slide 4: Saint Camillus Church Bell Tower Masonry Assessment
Engineering review
Exterior observations: cracked and spalled brick, failed sealants, efflorescence, failed interior mortar and structural wall ties, steeple roof repairs.
Interior observations: cracked and spalled brick, efflorescence, eroded mortar, concrete deck spalling and steel reinforcing erosion, failed sealants, deteriorated bird screen frames.

## Slide 5: Saint Camillus Church Bell Tower Masonry Assessment
Carillon shutdown
Due to safety concerns regarding vibration, the carillon chiming mechanism was disabled.

## Slide 6: Saint Camillus Church Bell Tower Masonry Assessment
Develop Scope of Work and Bidding
Scope of work was developed utilizing engineer’s recommendations.
Project bid to five qualified contractors, four bids received.
Low bid: Folan Waterproofing and Construction Co., Inc., September 2024
Assume four months construction

## Slide 7: Saint Camillus Church Bell Tower Masonry Assessment
CPARL Facilities Committee Oversight
Monthly visual review from grade with binoculars
Access bell tower and exterior review 31 December 2024
Removal of masonry debris March 2025
Access bell tower and exterior review 9 May 2025
Access bell tower and exterior review 12 September 2025

## Slide 8: Saint Camillus Church Bell Tower Masonry Assessment
Photographic documentation
December 2024
Masonry degradation and staining, East side
Interior masonry spalling

## Slide 9: Saint Camillus Church Bell Tower Masonry Assessment
Photographic documentation
December 2024
Spalled interior masonry debris at bell tower level
Spalled interior masonry & eroded mortar, sealant failure

## Slide 10: Saint Camillus Church Bell Tower Masonry Assessment
Photographic documentation
December 2024
Concrete deck deterioration below steeple
Rust jacking of concrete deck below steeple

## Slide 11: Saint Camillus Church Bell Tower Masonry Assessment
Photographic documentation
May 2025
Rust jacking of concrete deck and rebar deterioration below steeple
Masonry & sealant degradation at bell tower interior

## Slide 12: Saint Camillus Church Bell Tower Masonry Assessment
Photographic documentation
May 2025
Masonry degradation & eroded mortar at bell tower interior
Masonry and sealant degradation at bell tower interior

## Slide 13: Saint Camillus Church Bell Tower Masonry Assessment
Photographic documentation
September 2025
Masonry degradation, atmospheric staining at bell tower exterior
Masonry and sealant degradation, atmospheric staining at bell tower exterior

## Slide 14: Saint Camillus Church Bell Tower Masonry Assessment
Photographic documentation
September 2025
Masonry staining and sealant degradation at bell tower exterior
Spalling masonry and mortar failure, atmospheric staining at bell tower exterior

## Slide 15: Saint Camillus Church Bell Tower Masonry Assessment
Photographic documentation
September 2025
Masonry spalling and mortar failure, atmospheric staining at bell tower exterior
Masonry spalling and mortar failure at north chimney facade

## Slide 16: Saint Camillus Church Bell Tower Masonry Assessment
Photographic documentation
September 2025
Masonry degradation at bell tower
Masonry and sealant degradation at bell tower interior

## Slide 17: Saint Camillus Church Bell Tower Masonry Assessment
Photographic documentation
September 2025
Masonry and sealant degradation at bell tower
Rust jacking of concrete deck and rebar deterioration below steeple