UPDATE                             6-1-22

Status of Education Building Issues

St William Catholic Church, London, Ky

History

The education building was built in 1953 It is 68 years old.  It was originally designed with two class rooms, a cafeteria room, and living quarters on the upper floor. The lower floor was the church.  This is a well founded structural brick building with steel used for floor and roof supports and window lintels.  The original building was naturally ventilated (ie tall windows on the upper floors).   The core structure of the building is in excellent condition with no settlement noted.  Over the years various upgrades have been made to the building.  The natural ventilation windows were replaced with solid windows, HVAC units and duct work were added. When the new church was built four classrooms were added to the lower floor that was originally the church.  A new roof was installed in 2004 and the exterior painted. In 2013 the exterior of the building was repainted.. In 2016 the blackboards were upgraded to white, shades were added to all windows, a new modern security and fire alarm system was added, the internet with latest Wi-Fi was installed,  and various other items upgraded such as restroom floors.

Currently corrosion to the steel (particularly the ends) that is part of the window lintels is causing deterioration that sometime in the future will cause failure. This is predominant in the large front windows but is present in many of the small windows.  This is caused by moisture within the walls.  There is no through flashing of the windows which would be done today nor weep holes. The design and age of the roof also causes moisture ingestion.  The corrosion was discovered when the distortion of the brick at some of the window corners was noted.  The corrosion was causing the brick distortion from the back side and thus visible from the outside.

Available Funding

The Finance Council has advised that the allowable expenditure for this endeavor is $450,000.  This will not impact the financial stability of the parish.

Evaluations of Options

Based on a recommendation from the Finance Committee to the PPC(Parish Pastoral Council) a study group was established to develop and evaluate alternatives to repair of the building and stay within the $450,000 target.

Options

The following options were studied and estimated:

Option                          Description                       		Cost

1	Do Nothing						XXXX

2	Repair Existing Building				$ 768,000

3	New Building behind Existing Building		$ 829,000

(Demolish Existing Building)

4	New Building in front of Existing Building	$ 829,000

(Demolish Existing Building)

5	New Building in place of Existing Building	$ 829,000

(Demolish Existing Building)

6	Movable Hanging Partitions in Stern Hall		$ 448,000

7	Movable Floor Mounted Partitions in Stern Hall	XXXX

Decision Support Package

A decision support package was developed in the process of defining and estimating the options.  this included financial projections, risk assessment, and various configurations that would meet the needs of the parish.  this includes all the data utilized in corgin the available options.

Current Activities

The decision support package and options has been reviewed with the Parish Pastoral Council (PPC), the Finance Council and the Study Group.

Input from the congregation will be solicited from the congregation on June 7 amd 11.

Based on the above input, the Parish Pastoral Council will make a recommendation to t he Pastor and Bishoop Stowe. This will be developed at the PPC meeting or June 22.  The concurance of  the Finance Council will be solicited at this time.

An update to Bishop Stowe, the Secretariat for Stewardship, and the Diocesean Construction Committee with copies of the Decision Support Package.

Path Forward

Schedule a review with the Diocesean Construction committee in Early July.

Begin preparations for implementation of the decision with an anticipated date of approval by the end of August 2022.

Overall Schedule

It is anticipated that the project can begin firm activities by Sept 1, 2002.  If the partition option is chosen this would assure that the renovations to the basement would be completed to begin the Septembe 2023 school in the basement.  From Sept 2022 through May 2023 the clases would  take place in the existing building.