## General
Pledge Drive To-Do List - Spring 2018- Version 1.0 | Assigned | Complete | Comments
Pre-Pledge Drive
Two - Three Months Before
§ Pledge Drive goal = $____________
o Raise $______ in matching funds
o Recurring Monthly Donations = $______ X 6 months = $________
o Goal to raise $______ per day in new donations
o Coordinate Efforts with Development Advisory Board
o Secure Board Contributions
o Meet with Major Donors outside of Advisory Board
§ Theme = “________”
§ Develop Ad for Local Catholic Publications
§ Produce new or use old Testimonials or Stories of Faith to use in PD spots
§ Pre-Pledge Drive calls – Major Donors
§ EMAIL – Send general message regarding Pre-Pledge Drive
§ Schedule Local Bishop - Mass and studio
§ Schedule Priests - Masses for each day of Pledge Drive
§ Compile Guest/Priest Email List
§ Set up Sign Up Genius for Guests & Volunteers
§ Schedule Guests
§ Compile Volunteer Email List
§ Send email to past volunteers
§ Sign-up Volunteers
§ Sign-up Data-Entry Volunteers
§ Adoration and Rosary for the success of the Pledge Drive
§ Provide Catholic Radio Prayer to Adoration Chapel Coordinators
§ Phone set-up - Coordinate with OTT / Install 3 days ahead
§ Draft Thank You Letter - save in electronic folder
§ Review scripts and Pledge Card Info
§ Organize prayer groups for each day during Pledge Drive
§ Order Pledge Cards
Pledge Drive To-Do List - Spring 2018 | Assigned | Complete | Comments
Two - Three Months Before (continued)
§ Order thank you gifts
§ Gifts for Pledge Drive
o Monthly Donors and Monthly Increases
o Gift for Guests and Priests
o Gift for Volunteers
o Gift for all donors (300+) - Prayer Cards
o Gift for donors of Matching Gifts
§ Check supply of Remittance Envelopes / Reminder Cards / Bumper Stickers
§ Check supply of printer cartridges
§ Order needed supplies - Bumper stickers, letterhead, envelopes, etc.
§ Prepare show host spots in support of Pledge Drive
§ Prepare Pre-Pledge Drive Spots
§ Prepare Pledge Drive Spots
§ Guest Prep Kit - send to guests and priests
§ Build and Expand Knights of Columbus Council List and Contact
§ Build and Expand Parish Ambassador List and Contact
One Month Before
§ Begin Novena to St. Joseph
§ Develop splash page for website and post
§ Develop Custom Bulletin Inserts
§ Develop General Bulletin Announcements
§ Record and Air KC Time spots Pre-Pledge Drive
§ Begin airing spots for Pre-Pledge Drive
§ Materials needed for Pledge Drive
o Pledge Drive – Develop Call List and Mailing List
o Confidentiality Agreement for Volunteers
o CCM Emergency Numbers
o Phone Operator Script
o Instructions to Transfer Calls
o Volunteer Sign-up Sheets
o Instructions / Questions to prompt Testimonials - Post in several places
o Parish Ambassador Sign-up Sheets
§ Follow up with Knights of Columbus Councils
§ Follow up with Parish Ambassadors
§ Write EMAIL Messages - schedule in contact management system
§ Pre-Pledge Drive Mailing - identify target audience
§ Pledge Drive Call List – Develop / Organize Call Lists - add number the pages, freeze titles
§ Contact Parish Ambassadors to raise awareness in local parish
Pledge Drive To-Do List - Spring 2018 | Assigned | Complete | Comments
One Month Before (continued)
§ Order extra coffee and water
§ Pick up food and kitchen supplies
o Cups
o Plates
o Napkins
o Spoons
o Half n’ Half
o Sugar & Sweeteners
o Order Food for lunches
o Snacks
o Nuts
o Bring Platters
o Bring Tablecloths
§ K of C – one last publicity push
§ K of C – quick email to remind them of the PD
§ Confirm with Bishop's Office
§ Develop and send guest bios to PD Host w/ name pronunciations
§ Website updates and post
One Week before Pledge Drive
§ Name tags for volunteers and staff
§ Set up K of C call center - tables / chairs
§ Set up Materials at Phone Stations; refer to list above
§ Place Sample Cards and materials at phone stations
§ Copy Prayers of the Faithful for Masses during Pledge Drive
§ Reveiw Call Lists for Volunteers during Pledge Drive - one call during PD
§ Email Priests and Guests, schedule and instructions
§ Order lunch during PD
§ Social Networking and Communications Pre-Pledge Drive
o Facebook – Pre-Pledge Drive
o Develop Pre-Pledge Drive and Pledge Drive messages for EMAILS
o Twitter– Pre-Pledge Drive
§ Website updates and post - 6am / 12 noon / 5pm
§ Complete Talking Points
§ Finalize Thank You Letters
§ Write Thank You Mass Cards for Guests
§ Secure a Missal and all items needed for Bishop Deeley to celebrate Mass
§ Prepare signs to encourage volunteers to ask for Testimonials, Town & Phone if on donor in database
Pledge Drive To-Do List - Spring 2018 | Assigned | Complete | Comments
Pledge Drive Week
§ Follow up with each priest celebrating Mass
§ EMAIL to remind people about the Pledge Drive
§ Shop for perishable items
§ Test phones in call center and office phones
§ Change voicemail message to reflect Pledge Drive
§ Tidy up offices, kitchen, call center
§ Track recipients of all gifts by guest / by hour
§ Enter all pre-Pledge Drive pledges/gifts for Knights of Columbus
§ Change notifications for Payment Processing
§ Change the voicemail recording to the Pledge Drive message
During Pledge Drive
§ Pick up Hosts as needed
§ Begin with prayer e.g. 6:45AM
§ Prepare altar for Mass
§ Prepare studio / microphones for Mass
§ Make sure Phones are off "DO NOT DISTURB" in call center
§ Greet volunteers and check stations for supplies
§ All staff should introduce themselves and greet volunteers and guests
§ Greet priest and provide him with the Prayers of the Faithful for Mass
§ Refresh food and supplies in kitchen area
§ Call all donors who gave $250+ during slow times
§ Data Entry - Spreadsheet with running tally
§ Data Entry - Track Online Donations every hour
§ Data Entry for K of C hours - Wednesday
§ Data Entry for K of C run totals at the start of each day / noon / end of day
§ Data Entry – Coordinate volunteers
§ Data Entry – complete as much as possible each day
§ Coordinate volunteers making outbound calls during the Pledge Drive
§ Process all insta-charges – determine processing date
§ Process new donors, wait on existing donors if around 15th of the month
§ Prioritize thank you letters for donors sending in checks with instructions
§ Send remittance envelopes to check donors during Pledge Drive
§ Social Networking and Communications during Pledge Drive
o Facebook
o Emails – during Pledge Drive - specific messages on goal attainment
o Twitter– during Pledge Drive
o Take pictures and post during PD
§ Website updates and post
Pledge Drive To-Do List - Spring 2018 | Assigned | Complete | Comments
Post Pledge Drive
§ Data Entry - Sign up Volunteers
§ Post-Pledge Drive Announcements
§ Specific Announcements if Goal is not met
§ New Announcements when Goal is met
§ Thank You Letters and Gifts
§ Reminder Cards / Letters - go out 2 weeks after PD
§ Call all donors who gave $250+
§ Handwritten Thank You notes to all donors who gave $250+
§ Website updates and post
§ Compile final figures on spreadsheets in studio
§ Compare report final figures and check against spreadsheet totals
§ Send gifts announced during Pledge Drive - hourly or guest initiated
§ Send EMAIL on attainment of goal
§ Send email to volunteers - PD results
§ Send email to priests and guests - PD results
§ Send follow-up letters / reminder cards (30, 60, 90 days)
§ Update Volunteer Database
§ Change the Phone voicemail recording to general message